Competitive Tender for the Development of Tasersiaq and Tarsartuup Tasersua Hydropower Potentials and Connected 
Offtake Industry in Greenland

Request for Proposals

Contents

1.	Definitions	3

2.	Introduction	4

2.1	Background	4

2.2	Hydropower Potentials	5

3.	Framework for competitive TENDER process	6

3.1	Anticipated plan for the competitive tender process	7

3.2	Activities before bid submission	8

3.3	Bid submission	8

3.4	After bid submission	9

3.5	Fees	10

4.	Evaluation of bids	10

4.1	Selection process, requirements, criteria and weighting	11

4.2	Description of minimum requirements and evaluation criteria	13

4.3	Requirements for composition of Qualified Bidder	20

5.	Contracting and post-award	21

5.1	Hydropower License negotiation and approval process	21

5.2	Post-award requirements	21

5.3	Guarantees and penalties	22

6.	Warranties	22

7.	Appendices	22

Request for Proposals

for the Development of Tasersiaq and Tarsartuup Tasersua Hydropower Potentials and Connected Offtake Industry in Greenland

Definitions

| Applicant | A single legal entity acting individually (or potentially with support from other legal entities (External Support)) or a consortium of legal entities acting collectively when responding to this RfP. |
| --- | --- |
| Bid Submission Deadline | The date specified in Section 3.3.1, by when the bid is to be submitted by a Qualified Bidder at the latest. |
| DKK | Danish kroner (currency used in Greenland). |
| Hydropower License | License to exploit one or both Hydropower Potentials under section 5 of the Hydropower Act subject to conditions (License no. 20xx […] for Exploration and Exploitation of Hydropower Resources for Production of Electricity). |
| Hydropower Potentials | Tasersiaq (07.e) and Tarsartuup Tasersua (06.g). |
| IBA | Impact Benefit Agreement. |
| ICAA | Industrial and Commercial Activities Agreement. |
| Ministry | The Ministry of Business, Mineral Resources, Energy, Justice and Gender Equality. |
| Offtake Industry | Downstream offtake industry as defined in the ICAA. |
| Primary Lead | The Primary Member designated as such. |
| Primary Member | As applicable, the single legal entity acting individually or a legal entity being a consortium member of a Qualified Bidder, as described in Section 4.3 |
| Project | The development, financing, permitting, design, engineering, procuring, construction, testing, commissioning, ownership, operation and maintenance, as well as the decommissioning and/or transfer (in whole or in part) of the facilities. |
| Project Company | The company to be established as an A/S (public limited liability company) or ApS (limited liability company) in Greenland by the Winning Bidder to implement the Project in accordance with Section 8 of the Hydropower Act. |
| Project Partner | Developers, operators, investors, and/or any other entities that are deemed a Winning Bidder. |
| Qualified Bidder | An Applicant that meets the minimum qualification criteria as set forth in the RfQ and that is thereby eligible to participate in the competitive tender process for the award of the Hydropower License. |
| RfI | Request for Information. |
| RfP | Request for Proposals. |
| RfQ | Request for Qualifications. |
| Secondary Member | A legal entity being a consortium member of a Qualified Bidder that is not a Primary Member, as described in Section 4.3. |
| Winning Bidder | The Qualified Bidder that the Ministry determines to award the Hydropower License to, in accordance with the RfP. |

Introduction

This section provides an overview of the planned competitive tender process for the Hydropower Potentials, including a detailed description of the Hydropower Potentials and the types of projects envisioned by the Government of Greenland.

The competitive tender process is not subject to Act no. 6 of 12 June 2019 on the procurement of goods and services in public authorities and institutions or Act no. 9 of 2 December 2009 on tendering in the construction sector. However, the Ministry will act objectively and treat every Bidder equally creating a fair and transparent competetive process.

Background

A country of sea and ice, Greenland is home to vast hydropower resources, which have yet to be exploited. Summer melt-off from the ice cap feeds into large lakes that run off into fiords and the ocean. As a result of global warming, this has increased substantially in both speed and quantity. The Government of Greenland is determined to turn the consequences of climate change into a climate solution.

Greenland is moving towards zero-emission production of electricity. However, Greenland’s enormous untapped hydropower resources exceed the domestic demands many times over, and Greenland has the potential to become a net energy exporter.

In this regard, the Government of Greenland invites interested parties to submit project proposals and participate in an open, transparent, and competitive tender process for the development of hydropower resources in West Greenland.

By providing access to abundant renewable energy, the Government of Greenland seeks to attract power intensive industries with the potential to generate economic growth, employment and technological advancement. Due to the limited current electricity demand in Greenland, developing an offtake industry must be done as an integrated part of the Project.

Bids will be accepted from both companies that are capable of delivering the total value chain from energy production through to the offtake product, as well as from consortia of companies that in combination provide the same capability.

Hydropower Potentials

The two hydropower potentials – Tasersiaq (07.e) and Tarsartuup Tasersua (06.g) (hereinafter "Hydropower Potentials") – are located on the southwest coast between Kangerlussuaq and Nuuk. Together, they represent the largest and most thoroughly researched hydropower potentials in Greenland, with a combined capacity of approximately 1,100 MW and a firm energy output of around 9,600 GWh per year.

Estimates based upon hydrological time series show that Tasersiaq (07.e) has a potential of approximately 820 MW installed capacity, and Tarsartuup Tasersua (06.g) is estimated to sustain a capacity of approximately 280 MW.

Due to the topography of the land and seasonal inflow variations, the Hydropower Potentials can primarily be exploited using reservoirs and not as run-off-the-river hydropower plants. The Hydropower Potentials can be developed by damming up existing high-lying lakes, leveraging natural reservoirs located 650-700 meters above sea level. The catchment areas are connected to the inland ice, and most of the water resource comes from the ablation of the inland ice cap. The Hydropower Potentials are located close to seaways, and relevant seaways are, in general, accessible all year round.

The following map illustrates the areas reserved for the tender where the Hydropower Potentials are located (Figure 1).

Figure 1: Map of areas reserved for tender.

Framework for competitive TENDER process

The RfP contains specific information related to the bid submission and evaluation phase and will be issued to Qualified Bidders. A Qualified Bidder will be able to submit up to three separate bids, including:

- One bid for Tasersiaq (07.e), and/or

- One bid for Tarsartuup Tasersua (06.g), and/or

- One bid for both Hydropower Potentials combined.

The bid must include an Offtake Industry to utilize the energy produced.

Bid submissions will be judged by the Ministry against a set of defined minimum requirements. Only bids deemed to comply with these requirements will be moved forward to bid evaluation. The compliant bids will be assessed based on an evaluation framework, consisting of a set of qualitative and financial criteria, described in the RfP. A selection of bids will be shortlisted, and the winning bid will be the one with the highest evaluation among them.

A deposit of DKK twenty-five million (DKK 25,000,000) must be paid upon bid submission. The deposit will be retransferred to all Qualified Bidders after the award, with one exception; if the Winning Bidder withdraws before signing the binding project agreement, which consists of the Hydropower License, the deposit will be lost.

The Winning Bidder will sign the Hydropower License. The Hydropower License gives the Winning Bidder a right to test, validate and further develop the initial concept during the Proof of Concept phase. It also gives a right to start construction and a right to exploit hydropower, on condition that all necessary approvals and permits have been secured, including agreements such as the IBA and the ICAA. The Winning Bidder is obligated to pay a defined license fee.

If the necessary approvals and permits are not obtained, or the Project is not deemed sufficiently attractive by the Winning Bidder, it will have a right to withdraw from the Project during the Proof of Concept phase upon a payment of liquidated damages equal to DKK thirty million (DKK 30,000,000). In the case of withdrawal, the Ministry holds the right to publish all data obtained from studies conducted during the Proof of Concept phase and has the right to re-tender the Hydropower Potentials.

The Winning Bidder will need to secure all necessary permits before an agreed deadline. If this deadline is not met, the Hydropower License is reverted to the Ministry.

Anticipated plan for the competitive tender process

The following table outlines the anticipated milestones and process for the competitive tender process.

Table 1: Anticipated plan for the competitive tender. process.

The anticipated process outlined in this Section is for forward guidance purposes only, and it should be noted that timings may be subject to change.

Activities before bid submission

Site visits

The Qualified Bidders have the possibility to conduct site visits during [Date]. All costs incurred in connection with the site visit must be paid by the Qualified Bidders.

Release of final RfP

After receiving feedback to the RfP and the draft Hydropower License, the Ministry will review the received feedback and further develop the RfP and Hydropower License.

The release of the final RfP on [Date].

The Ministry reserves the right not to take into account the feedback received.

Questions & answers

Any clarification questions arising from the documents, including this RfP, which may have a bearing on the bid submission, should be raised in writing to:

Abeline Bentzon-Tarp and Maja Heegaard

hydropower@nanoq.gl

Energy Department

The Ministry of Business, Mineral Resources, Energy, Justice and Gender Equality

Postbox 1601, 3900 Nuuk, Greenland

Telephone: +299 34 50 00

Email: hydropower@nanoq.gl

The Ministry will endeavour to respond to all clarification questions as soon as possible. All such queries received, together with the Ministry’s responses, will be circulated to all Qualified Bidders. Notwithstanding this general position, there may be occasions where the Ministry considers the clarification question or its response to be commercially sensitive and, as such, the Ministry reserves the right to anonymize the question and response or to respond only to the Qualified Bidder raising the particular clarification question.

The Ministry will do its utmost to respond to any question or request but might not be able to answer all questions given the late stage at which they are submitted and as such reserves the right not to respond to any question or request.

Bid submission

Submission instructions

The evaluation of submitted bids in accordance with the criteria will be conducted based on a method consisting of two steps: i) a pass/fail assessment of minimum requirements, and ii) an evaluation of the Qualified Bidder(s) based on the evaluation criteria.

First, the Qualified Bidders must demonstrate that they meet the minimum requirements. Qualified Bidders that meet the minimum requirements will then be evaluated based on the evaluation criteria. A Qualified Bidder must also meet the same requirements as specified in the RfQ with regards to the composition of Primary Members and Secondary Members.

A Qualified Bidder will be able to submit up to three separate bids, including:

- One bid for Tasersiaq potential (07.e), and/or

- One bid for Tarsartuup Tasersua (06.g), and/or

- One bid for both Hydropower Potentials combined.

The Qualified Bidder must submit the bid to:

Abeline Bentzon-Tarp and Maja Heegaard

hydropower@nanoq.gl

Energy Department

The Ministry of Business, Mineral Resources, Energy, Justice and Gender Equality

Postbox 1601, 3900 Nuuk, Greenland

Telephone: +299 34 50 00

Email: hydropower@nanoq.gl

All documents must be submitted in pdf format.

The Qualified Bidder must submit complete information to the Ministry by [Date] (“Bid Submission Deadline”).

After the Bid Submission Deadline, no changes can be made to the bid, except for any additional information/queries that may be required. The Qualified Bidder must submit all additional information if requested by the Ministry during the review of the bid.

Bids may not contain deviations, reservations, or ambiguities in relation to the documents. The Ministry may, in exceptional circumstances decide to accept a Bid Submission which contains slight deviations, reservations or ambiguities from the tender documents, provided that such a decision does not favor one Qualified Bidder over another.

Bid deposit requirements

A deposit of DKK twenty-five million (DKK 25,000,000) must be paid upon bid submission. The deposit will be retransferred to all Qualified Bidders after the award, with one exception; The deposit will be retransferred to all Qualified Bidders after the award, except in a case where the Winning Bidder withdraws before contract signing.

After bid submission

Completeness check

The Ministry has prepared a “Completeness Checklist” which is a tool to help Qualified Bidders assess whether a bid is complete.

To assist in preparing bids, the Completeness Checklist summarizes the requirements outlined in Section 4. Each Qualified Bidder must submit a completed Completeness Checklist as an Excel file, using the provided template, and named [X].

The Completeness Checklist is merely a tool to help Qualified Bidders assess whether a bid is complete. As such the Qualified Bidder is solely responsible for submitting a bid that meets the minimum requirements and other requirements in the competitive tender process.

As mentioned in Section 3.3.1, bids may not contain deviations, reservations, or ambiguities in relation to the tender documents. The Ministry may, in exceptional circumstances decide to accept a bid which contains slight deviations, reservations or ambiguities from the tender documents, provided that such a decision does not favor one Qualified Bidder over another.

Request for clarifications

During the evaluation of submitted bids, the Ministry may identify areas that require further information or clarification.

Where the information, documentation of requirements or documents submitted by any Qualified Bidders in connection with a submitted bid are incomplete, incorrect or if specific documents are missing, the Ministry may, during the evaluation of submitted bids, request any Qualified Bidder to supplement, clarify, amend or complete the submitted bid by submitting relevant information or documentation within an appropriate deadline and in an appropriate format set by the Ministry.

All materials and statements provided during this process will be considered binding.

The Ministry is under no obligation to seek clarification of any aspect of a bid and reserves the right to disregard any unsolicited or impermissible clarification, but the Ministry will treat all bidders equally.

Fees

The following non-refundable fees will be payable during the competitive tender process:

- DKK two hundred and fifty thousand (DKK 250,000) excl. VAT per Applicant to receive a copy of this RfQ, including a right to submit a qualification application (single fee per Applicant);

DKK two million five hundred thousand (DKK 2,500,000) excl. VAT per Qualified Bidder to receive a copy of the RfP (single fee per Qualified Bidder); and

DKK five hundred thousand (DKK 500,000) excl. VAT per individual bid submitted by a Qualified Bidder (fee per bid per Qualified Bidder).

The fees outlined in this Section are charged in accordance with Section 12(1) of the Hydropower Act.

Evaluation of bids

This Section outlines the selection process that will be conducted during the competitive tender process for the Project. It also details the minimum requirements and evaluation criteria that Qualified Bidders will be assessed against, and the associated documentation requirements.

Selection process, requirements, criteria and weighting

The evaluation of submitted bids in accordance with the criteria will be conducted based on a method consisting of two steps: i) a pass/fail assessment of minimum requirements, and ii) an evaluation of the Qualified Bidder(s) based on the evaluation criteria.

First, the Qualified Bidders must demonstrate that they meet the minimum requirements. Qualified Bidders that meet the minimum requirements will then be evaluated based on the evaluation criteria. The Qualified Bidder that obtains the highest evaluation when considering all evaluation criteria, will become the Winning Bidder and awarded the Hydropower License.

The minimum requirements, evaluation criteria and the weighting of each criterion are shown in Table 2. Some criteria include both a minimum requirement and an evaluation criterion, and this is further elaborated in Section 1.1.

Table 2: High-level requirements- and criteria overview for the Project.

| Category | Criteria | Minimum requirements | Evaluation criteria | Weight |
| --- | --- | --- | --- | --- |
| 1) Environment | A) Environmental impact | X |  | Pass/fail |
|  | B) Climate impact | X |  | Pass/fail |
| 2) Human capital | A) Working conditions and HSE | X |  | Pass/fail |
|  | B) Upskilling of local labor | X | X | 5% |
| 3) Social impacts | A) Social/cultural impacts from the Project | X | X | 5% |
|  | B) Impacts on local infrastructure and social services | X | X | 5% |
|  | C) Energy to serve Greenlandic demand |  | X | 5% |
| 4) Localization | A) Growth of local economy | X |  | Pass/fail |
| 5) Deliverability | A) Concept and funding plan | X |  | Pass/fail |
| 6) Financial | A) Revenue to the Government of Greenland | X | X | 65% |
| 7) Exploitation of potentials | A) Energy production |  | X | 10% |
|  | B) Use of excess heat |  | X | 5% |
| 8) Risk to Greenland | A) Risk from Project to Greenland | X |  | Pass/fail |

Description of minimum requirements and evaluation criteria

Table 3: Description of minimum criteria.

| Category | Criteria | Documentation requirement |
| --- | --- | --- |
| 1) Environment | A) Environmental impact The Qualified Bidder must have a clear plan to mitigate negative environmental impacts such as, but not limited to, water pollution, air pollution, impacts on land biodiversity, sea biodiversity, and land degradation in line with Greenlandic environmental laws. Minium criterion: The Qualified Bidder will be assessed based on the quality of the plan, including suggested measures, and documented experience from similar work. The Winning Bidder will later detail this plan in an Environmental Impact Assessment (EIA). | - Plan for environmental impact mitigation, including concrete measures to address potential impacts. - Description of experience with environmental impact mitigation in similar projects. Maximum four (4) pages |
|  | B) Climate impact The Qualified Bidder should strive to mitigate climate gas emissions from the Project. Minimum criterion: The Qualified Bidder must document that the end-product produced by the Offtake Industry will have lower climate gas emissions compared to the world average for similar products, and a realistic plan to mitigate the climate gas emissions. | - Assessment of the climate footprint of end-products (CO2e/unit) according to ISO standard 14040 and 14044 - Plan describing actions to mitigate climate footprint Maximum four (4) pages (calculations can come in addition as an appendix) |
| 2) Human capital | A) Working conditions and HSE Minimum criterion: The Qualified Bidder must have sufficient systems for quality assurance, HSE and internal control for the Project, compliant with the Greenlandic labor laws. | - Documentation of planned systems for quality assurance, HSE and compliance for the Project. Maximum two (2) pages |
|  | B) Upskilling of local labor The Qualified Bidder must have a long-term plan for educating/upskilling and employing the local workforce in Greenland. Minimum criterion: The Qualified Bidder must within the first [10] years of operation employ a minimum of [20%] local workers. Evaluation criterion: The evaluation will be based on the annual number of blue-collar local workers the Qualified Bidder commits to train for more than [6] months, and later full-time employ at the hydropower plant or in the Offtake Industry. | - Description of the planned training/ upskilling of the Greenlandic workforce, including plan to employ the minimum fraction of Local workers. - Commitment on the annual number of blue-collar workers the Qualified Bidder will train. Maximum four (4) pages |
| 3) Social impacts | A) Social/cultural impacts from the Project Minimum criterion: The Qualified Bidder must have a clear and realistic plan for mitigating potential negative impacts on local societies and the Greenlandic culture through all stages of the Project, and particularly addressing the potential challenges from large-scale labor immigration. Evaluation criterion: The quality and realism of the proposed plan will be evaluated considering the Qualified Bidder’s experience from mitigating negative social/cultural impacts in similar projects. | - Plan describing the actions to mitigate potential negative social/cultural impacts from the Project - Description of previous experience on mitigating negative social/cultural impacts in similar projects (maximum two (2) projects) Maximum four (4) pages |
|  | B) Impacts on local infrastructure and social services The Qualified Bidder must take responsibility for sufficient infrastructure for workers and their families, such as, but not limited to, housing of workers, water, heat, electricity and waste management, and social services such as medical services and educational services, throughout the lifetime of the Project. This can be done through measures such as co-financing of infrastructure/social services provided by the Government of Greenland, and through private initiatives coordinated with the Government of Greenland. Minimum criterion: The Qualified Bidder must have a clear and realistic plan for providing sufficient infrastructure and social services for the workers involved in the Project. Evaluation criterion: The quality and realism of the proposed plan will be evaluated considering the Qualified Bidder’s experience from providing required infrastructure and social services for workers in similar projects. | - Plan for providing required infrastructure and social services for workers. - Description of previous experience on providing required infrastructure and social services for workers from similar projects (maximum two projects). Maximum four (4) pages |
|  | C) Energy to serve Greenlandic demand The ability of the Qualified Bidder to serve Greenlandic energy demand, will depend on project concept, and proposed location of Offtake Industry. No minimum requirements are set for this dimension, but Qualified Bidders can differentiate in the competitive tender process by serving Greenlandic energy demand. Three main dimensions are viewed as relevant for serving Greenlandic energy demand: - Electricity for local demand - Heat for local demand - Clean fuels to serve demand in Greenland Evaluation criterion: The average annual expected energy amount (MWh) planned to be supplied for Greenlandic energy demand (end-use). The estimate should be deemed realistic, given the current demand, and projections on future demand. | - Description of how the Project will serve Greenlandic energy demand, including which energy dimensions will be included. - Estimated amount of energy that will be supplied each year of the Project lifetime. Maximum two (2) pages |
| 4) Localization | A) Growth of Greenlandic economy The Qualified Bidder should ensure that the Greenlandic economy benefits from the Project, without driving demand for products and services unsustainably high, which could lead to price inflation. Local suppliers should generally be used when applicable, but sourcing from them should take into account the tight labor market in Greenland, and the limited number of relevant suppliers in proximity to the Hydropower Potentials. Minimum criterion: A description of how Local suppliers will be involved sustainably in the Project to benefit the local economy. | - Plan for sustainable involvement of local suppliers throughout the project lifetime. Maximum two (2) pages |
| 5) Deliverability | A) Concept and funding plan The Qualified Bidder must have a realistic Project concept, including both hydropower plants and Offtake Industry, with a well-defined interface between the upstream power production and the downstream power consumption Minimum requirements: - The technical concept, including cost estimates must be realistic. - The commercial concept, including the interfaces in a potential consortium must be well-defined. - The plan for obtaining sufficient funding must be realistic, optimally including commitment from funding institutions. The funding plan must include equity in the Project Company corresponding to at least 20% of the Project’s estimated investment cost. - The most important risks impacting the business case of the Project must be mapped out, with realistic actions proposed to mitigate the risks. The quality and realism of the proposed hydropower- and Offtake Industry concept and plan will be assessed considering the Qualified Bidder’s experience with similar projects. Recent experience within the following dimensions will be deemed positive: - Experience with large hydropower plants of similar size and design as the proposed concept (tunnel type, rock type, fiord outlet, station type, etc.). - Experience with offtake projects of similar size and design as the proposed concept. - Experience with projects in Arctic conditions, including permafrost. - Experience with self-supplied construction sites in remote areas without proximity to infrastructure. | - Description of the technical concept and operating model, including location of hydropower production, Offtake Industry and all relevant infrastructure (dams, tunnels, roads, power plants, transmission lines, ports, industry buildings, etc.) - Overview of the estimated investments and operating expenses during the lifetime of the hydropower assets, and the estimated electricity production (P50 and P90). The resulting Levelized Cost Of Electricity (LCOE) generated from the hydropower plant must be calculated for the entire lifetime of the Project (P50 and P90). A discount rate corresponding to the hurdle rate applied in the Qualified Bidder’s business case must be applied. - Description of the commercial concept of the Qualified Bidder (business case, route to market for end-product, and potential customers), and which companies will be responsible for each step of the value chain - Funding plan for the end-to-end Project, specifying project budget, including the equity distribution between companies if the Qualified Bidder is a consortium. - Risk assessment, where the Qualified Bidder describes key risk factors and planned strategy for mitigating these. - Description of relevant experience with similar projects. Maximum fifteen (15) pages (any agreements and calculations can come in addition as an appendix) |
| 6) Financial | A) Revenue to the Government of Greenland [Pending government take model decision] [Potentially: Magnitude of annual license fee] [Potentially: PPA-price for Offtake Industry] | [WIP – pending government take model decision] |
| 7) Exploitation of potential(s) | A) Energy production The Qualified Bidder should aim to maximize the energy production from the Hydropower Potential(s), taking into account the likely increase in inflow in catchment areas during the lifetime of the assets. This should not be performed at the expense of the financial and environmental sustainability of the Project Evaluation criteria: The average annual expected energy production (GWh) from the Hydropower Potential(s) during the lifetime of the assets should be maximized, while ensuring a sustainable project. | - Calculation of the average annual expected energy production from the Hydropower Potential(s) during the lifetime of the assets. The base case scenario in the report [Asiaq – Predicted future (2023-2100) water resource at hydropower potential 06.g and 07.e in Southwest Greenland] must be used as basis for available inflow for each potential each year. Maximum two (2) pages |
|  | B) Use of excess heat The Qualified Bidder should strive to leverage potential excess heat from the hydropower plant and Offtake Industry for new industrial/commercial purposes (e.g., vertical farming, fish farming, manufacturing). Industrial/commercial concepts can either be developed by the Project Partner, or through agreements with other entities. Evaluation criteria: The amount of excess heat from the hydropower plant and industry (subtracted potential heat delivered to existing local demand) exploited in new industrial/commercial concepts. | - Assessment of excess heat generated in hydropower plant and Offtake Industry (GWh). - Plan for leveraging excess heat in new industrial/commercial concepts, including estimates for the amount of the excess heat consumed by these concepts. Maximum two (2) pages (any calculations can come in addition as an appendix). |
| 8) Risk to Greenland | A) Risk from Project to Greenland The Project must not pose a risk to Greenland’s national security, international relations or reputation. These risks must be assessed by both the Qualified Bidder and the Government of Greenland. Minimum requirements: The Qualified Bidder must evaluate potential risks to Greenland from the Project and have sufficient mitigation actions in place. The Government of Greenland will perform a separate risk assessment of the Project, and the risk imposed to Greenland must be deemed acceptable for the Project to fulfill the minimum requirement. | - Assessment of potential risks to Greenland within the dimensions of security, international relations or reputation from the Project, and proposed mitigation actions Maximum two (2) pages |

Requirements for composition of Qualified Bidder

A Qualified Bidder must also meet the same requirements as specified in the RfQ with regards to the composition of Primary Members and Secondary Members.

A Qualified Bidder must be composed of at least one Primary Member and may include Secondary Members. Primary and Secondary Members are required to meet certain equity commitments specified in the following paragraphs.

Each Qualified Bidder must designate one of its Primary Members as Primary Lead. The Primary Lead will be deemed to have been authorized by the other members of the Qualified Bidder to be responsible for all interaction with the Ministry.

All Primary Members and Secondary Members shall collectively demonstrate the extent to which they meet the minimum qualification criteria. When a Primary Member is assessed on an individual basis, this is expressly stated.

Shareholding requirements

Each Primary Member will be required to hold at least twenty percent (20%) of the shares in the Project Company during the period between the Effective Date [and a defined Production Milestone Date]. There can therefore be no more than five Primary Members of a Project Company.

All Primary Members collectively (or in case of a single Primary Member) will be required to hold more than fifty percent (50%) of the shares in the Project Company during the period between the Effective Date [and a defined Production Milestone Date].

There are no minimum shareholding requirements for the Secondary Member(s). However, all shares must be owned by either Primary Members or Secondary Members.

Table 4 provides an overview of the minimum shareholding requirements of the shareholder(s) in the Project Company as specified above.

Table 4: Minimum shareholding requirements.

| Minimum shareholding requirements during the period between the Effective Date [and a defined Production Milestone Date] |  |
| --- | --- |
| Each Primary Member | ≥ 20% |
| All Primary Members collectively | > 50% |

Change in composition of Qualified Bidder

If the Qualified Bidder is a consortium, it does not need to be formally constituted for the submission of the qualification application, as long as the consortium fulfills the minimum requirements of the RfQ. However, any subsequent change in the composition of the Qualified Bidder must happen no later than [one] month prior to the submission of the bid and will be subject to the Ministry’s written approval and following a re-evaluation of the Qualified Bidder’s qualifications. The re-evaluation will require the Qualified Bidder to submit:

- information required in item Fejl! Henvisningskilde ikke fundet. in the RfQ in all cases;

- information required in item Fejl! Henvisningskilde ikke fundet. to Fejl! Henvisningskilde ikke fundet. in the RfQ to the extent that the change in the consortium’s composition results in any change to the Primary Members or Secondary Members; and

- a Confidentiality Undertaking and evidence of payment of the fees specified in Section Fejl! Henvisningskilde ikke fundet..

Contracting and post-award

The post-award phase begins after a winner of the competitive tender process is determined and when the Ministry notifies the Winning Bidder of its intent to engage in commercial negotiations.

The Winning Bidder will be subject to post-award requirements which include the obtaining of approval for construction and operations, including agreements such as the IBA, ICAA, EIA, SIA and other reports. Please refer to Article 4-13 in the Hydropower License, for further information.

Hydropower License negotiation and approval process

After the Ministry notifies the Winning Bidder of the award of the Hydropower License, the finalization of the contract will be completed by the Ministry along with the Winning Bidder. The negotiation and approval process will take place during the course of [three months] from the date where the Ministry notifies the Winning Bidder of its intent to engage in negotiations. During this process, the following terms may be negotiated:

- [Terms to be negotiated are yet to be determined.]

The negotiations will focus on timelines and deadlines to be met, on minor changes etc. The negotiations cannot result in the Winning Bidder changing or amending its submitted bid in a way that is not favorable to the Ministry.

The Ministry reserves the right to engage in negotiations and conclude the Hydropower License with the Qualified Bidder, who has submitted the next best bid, if the Hydropower License is not signed no later than [three months] from the date where the Ministry notifies the Winning Bidder.

No legal relationship will exist between the Ministry and a Winning Bidder until a binding contract, i.e. the Hydropower License, is formally signed by both parties.

Post-award requirements

After signing the Hydropower License, the Winning Bidder must obtain approval for construction and operations, including agreements such as the IBA, ICAA, EIA, SIA and other reports. This is further described in detail in the Hydropower License. Please refer to Articles 4-13 in the Hydropower License.

Guarantees and penalties

The Winning Bidder will sign the Hydropower License. The Hydropower License gives the Winning Bidder a right to test, validate and further develop the initial concept during the Proof of Concept phase. It also gives a right to start construction and a right to exploit hydropower, on condition that all necessary approvals and permits have been secured, including agreements such as the IBA and the ICAA. The Winning Bidder is obligated to pay a defined license fee.

If the necessary approvals and permits are not obtained, or the Project is not deemed sufficiently attractive by the Winning Bidder, it will have a right to withdraw from the Project during the Proof of Concept phase upon a payment of liquidated damages (see Article 34.05 in the draft Hydropower License for penalty). In the case of withdrawal, the Ministry holds the right to publish all data obtained from studies conducted during the Proof of Concept phase and has the right to re-tender the Hydropower Potentials.

If the Winning Bidder withdraws from the Project after the Proof of Concept phase but withdraws prior to operations of the Project, the Winning Bidder can withdraw upon a payment of damages to the Government of Greenland (see Article 34.06 in the draft Hydropower License for penalty).

If the Winning Bidder withdraws from the Project prior to reversion, the Winning Bidder can withdraw upon a payment of damages to the Government of Greenland (see Article 34.07 in the draft Hydropower License for penalty).

Warranties

- By submitting a bid, a Qualified Bidder warrants that:

  - it is responsible for all costs and expenses related to the preparation and submission of its bid, any subsequent negotiation, and any future process connected with or relating to the RfP;

  - except as expressly stated in its bid, it otherwise accepts and will comply with the rules set out in this RfP;

  - it has sought and examined all necessary information which is obtainable by making reasonable enquiries relevant to the risks and other circumstances affecting its Proposal;

  - it has otherwise obtained all information and advice necessary for the preparation of its Proposal; and

  - […]

- it is satisfied as to the correctness and sufficiency of its bid.

Appendices

| Appendix 1 | Draft Hydropower License |
| --- | --- |
| Appendix 2 | ICAA |
| Appendix 3 | Bid form |
| Appendix 4 | Completeness Checklist |
| Appendix 5 | […] |

Relevant unit to be selected by the Qualified Bidder according to standard for end-product

If concrete companies are not defined for particular steps in the value chain, types of companies that could potentially be relevant must be described

Heat for local demand will be evaluated under criterion 3C